## Sheet1
Date | Time (Hours) | Work Type | Communication Method | Parties Involved | Description
2019-01-15 | 1 | research | In-Person | Mr. Ken Coburn, Scoutmaster Chris Schultz; David Killeffer | Discussion of possible project idea work at the American Legion, Abington MA
2019-01-22 | 1 | research | In-Person, email | Mr. Ken Coburn, Scoutmaster Chris Schultz; David Killeffer | Discussion of possible project idea work at the American Legion, Abington MA
2019-01-25 | 1 | project proposal work | No communication | Luke Killeffer | Simpifying workload into feasable project
2019-01-26 | 1 | project proposal work | No communication | Luke Killeffer | Simpifying workload into feasable project
2019-01-27 | 2.5 | project proposal work | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer | Simpifying workload into feasable project, proposal development
2019-01-28 | 4.5 | project proposal work | email | Mr. Ken Coburn, Scoutmaster Schultz, Mr. Chase, David Killeffer, Mark Jennings, Luke Killeffer | Simpifying workload into feasable project, proposal development
2019-01-29 | 1.1 | project proposal work | In-Person, email | Mr. Ken Coburn, Scoutmaster Schultz, Mr. Chase, David Killeffer, Mark Jennings, Luke Killeffer | Simpifying workload into feasable project, proposal development
2019-01-31 | 3 | project proposal work | No communication | Luke Killeffer | Simpifying workload into feasable project
2019-02-02 | 4 | project proposal work | No communication | Luke Killeffer | Simpifying workload into feasable project
2019-02-04 | 1.5 | project proposal work | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Simpifying workload into feasable project
2019-02-05 | 1.5 | finalizing Proposal and Submitting it | In-Person | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Finalizing proposal and turning it in to superiors to review
2019-02-10 | 0.25 | project proposal work | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Scheduling time for beginning of project
2019-02-15 | 0.25 | project proposal work | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Scheduling time for beginning of project
2019-02-16 | 4 | Clearing/sorting debris in Circle room/Attic | In person/Email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | working on project and preparing rooms for renovation
2019-02-18 | 0.25 | Taking Trash out of Attic | In-Person | Troop (Names are on sign in sheet) | Taking Trash out of Attic
2019-02-19 | 0.5 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer, J.C's Things, Dark Horse Antiques | Finding an Antique shop that is willing to look at stuff gathered at Legion to sell
2019-02-19 | 3.75 | trash removal from Circle Room | In-Person | Luke Killeffer, Mike O'Leary, Steven MacCormack, Liam Murphy, Nicholas Fitzgerald, Leo Tenore, Daniel Hannah, Peter Killeffer, Ben Killeffer, Owen Bechtold, Joe Cotter, Jimmy Cotter, Hunter Pinaud, John Aiello | Taking Trash out of Attic
2019-02-20 | 3 | research | No communication | Luke Killeffer | Researching Antique shops and scrap yards
2019-02-26 | 3 | Attic Cleanup | In-Person | Luke Killeffer, Mike O'Leary, Nicholas Fitzgerald, Owen Bechtold, Daniel Hannah, Steven MacCormack, Leo Tenore, Ben Killeffer, Liam Murphy, Peter Killeffer, Jonathan Killeffer, Jayden Bartrug, Arthur Sugarman, Jo LoCicero, Skye Manley, Hunter Pinaud, Ryan Murray | Taking Trash out of Attic
2019-03-05 | 1.5 | Attic Cleanup | In-Person | Luke Killeffer | Taking Trash out of Attic
2019-03-12 | 4 | Attic Cleanup | In-Person | Luke Killeffer, Will Mullen, TJ Joseph, Tim Pozerski | Taking Trash out of Attic
2019-03-19 | 3 | Attic Cleanup | In-Person | Luke Killeffer, Tim Pozerski, Andrew Roy, Justin Maskell, TJ Joseph, Will Mullen | Taking Trash out of Attic
2019-03-26 | 0.5 | Attic Cleanup | In-Person | Luke Killeffer | Taking Trash out of Attic
2019-04-06 | 7 | Taking Trash out of Attic and Scrapping Metal | In Person | Luke Killeffer, David Killeffer | Scrapping Metal and taking trash out
2019-04-02 | 0.25 | research | email | Luke Killeffer, David Killeffer | Finding an Antique shop that is willing to look at stuff gathered at Legion to sell
2019-04-02 | 0.5 | Taking Trash out of Attic | In-Person | Luke Killeffer | Take trash out of Circle Room to dumpster
2019-04-04 | 1 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer, J.C's Things, Dark Horse Antiques | Finding an Antique shop that is willing to look at stuff gathered at Legion to sell
2019-04-12 | 0.5 | research | email | Luke Killeffer, David Killeffer, Dark Horse Antiques | Finding an Antique shop that is willing to look at stuff gathered at Legion to sell
2019-04-15 | 1.5 | project communication | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Project status updates, discussion about issues blocking project progress (water damage issue, stinging insect issue, structural issues)
2019-04-17 | 1 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Project scheduling
2019-04-18 | 0.25 | research | email | Luke Killeffer, David Killeffer | Working on measurements for circle room plans
2019-05-06 | 0.5 | research | email | Luke Killeffer | researching door options for circle room
2019-05-22 | 0.5 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | researching door options for circle room
2019-05-26 | 0.5 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | researching door options for circle room
2019-05-28 | 0.25 | research | email | Luke Killeffer, David Killeffer | researching door options for circle room
2019-05-29 | 0.25 | research | email | Luke Killeffer, David Killeffer | researching door options for circle room
2019-05-30 | 2 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Researching Antique shops and scrap yards
2019-05-31 | 1 | discussion | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | confirmation on work days
2019-06-03 | 1 | research | email | Mr. Ken Coburn, Scoutmaster Schultz, Luke Killeffer, David Killeffer | Researching Antique shops, scrap yards and door options
2019-06-04 | 1 | discussion | email | Mr. Ken Coburn, Luke Killeffer, David Killeffer | Discussing with antique shops at Legion
2019-06-05 | 1 | discussion | email | Mr. Ken Coburn, Luke Killeffer, David Killeffer | Discussing with antique shops at Legion
2019-06-06 | 0.25 | discussion | email | Mr. Ken Coburn, Luke Killeffer, David Killeffer | report on current status of the attic
2019-06-09 | 3.5 | research | email | Luke Killeffer, David Killeffer | Researching possible door options for ciricle room
2019-06-13 | 1 | discussion | email | Luke Killeffer, David Killeffer | Discussing possible work days
2019-06-16 | 1 | research | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | Discussing possible work days
2019-06-17 | 0.5 | discussion/research | email | Luke Killeffer, David Killeffer | Researching and discussing a possible spaghetti fundraiser
2019-06-25 | 0.25 | research | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | Researching possible door options for ciricle room
2019-07-10 | 30 | Attic Cleanup | In-Person | Luke Killeffer, Sarah Killeffer, Peter Killeffer, Jonathan Killeffer, Benjamin Killeffer | Taking Trash out of Attic, bringing donation items to curb
2019-07-11 | 1 | discussion | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | discussing progress in attic and circle room
2019-07-12 | 0.25 | discussion | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | discussing progress in attic and circle room
2019-07-13 | 36 | Attic cleanup | In-Person | Luke Killeffer, David Killeffer, Sarah Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer, Madison Killeffer, Thomas Killeffer | Attic item cleanup, breaking apart junk, trash removal
2019-07-14 | 0.25 | research | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | Discussing possible work days
2019-07-22 | 0.25 | discussion | email | Luke Killeffer, David Killefer, Mr. Ken Coburn | progress update on dumpster
2019-08-05 | 1 | research | email | Scoutmaster Schultz, Luke Killeffer, David Killeffer | Discussing possibility of using plastic placard from the cage for eagle scout fundraiser
2019-08-05 | 2 | research | In-Person, email | Luke Killeffer, David Killeffer, Sarah Killeffer | Planning Fundraiser and emailing people to help with planning
2019-08-06 | 12.5 | Fundraiser | In-Person | Luke Killeffer, Madison Killeffer, Jonathan Killeffer, Thomas Killeffer, Peter Killeffer | Door to door fundraising in Neighborhood
2019-08-06 | 0.5 | discussion/research | email | Luke Killeffer, David Killeffer, Mr. Schutlz | Discussing materials needed for fundraiser and who will provide them
2019-08-06 | 1 | Fundraiser research | Phone | Luke Killeffer, Sarah Killeffer, Bill Mullen | Setting up a schedule to do fundraiser at lowes
2019-08-07 | 11 | Fundraiser | In-Person | Luke Killeffer, Madison Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer | Selling Chocolate Bars to the Neighborhood for fundraiser
2019-08-08 | 0.5 | discussion/research | email | Luke Killeffer, David Killeffer, Mr. Schutlz, Mr. Coburn | Discussing materials needed for fundraiser and who will provide them
2019-08-08 | 4 | Fundraiser | In-Person | Luke Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer | Selling Chocolate Bars to the Neighborhood for fundraiser
2019-08-09 | 2 | Fundraiser | In-Person | Luke Killeffer, Peter Killeffer | Selling Chocolate Bars to the Neighborhood for fundraiser
2019-08-10 | 0.25 | fundraiser | email | Luke Killeffer, David Killeffer, Mr. Schutlz | discussing fundraiser and sponsoring it
2019-08-10 | 72 | Fundraiser | In-Person | Luke Killeffer, Madison Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer, Sarah Killeffer, David Killeffer, Robert Killeffer | Selling Chocolate Bars at Lowes and cleaning up Legion Attic
2019-08-11 | 0.25 | Project | In-Person, email | Luke Killeffer, David Killeffer, Mr. Schutlz, Mr. Coburn | discussing if troop could help with cleaning attic for project
2019-08-11 | 2 | Project Communication | Email | Luke Killeffer, David Killeffer, Sarah Killeffer, Mr. Coburn, Mr. Schultz, Joe Thompson | Sending emails to give progress update on what the attic looks like and how much funds were raised
2019-08-13 | 1 | Project | In-Person, email | Luke Killeffer, David Killeffer, Mr. Schutlz, Mr. Coburn | discussing if troop could help with cleaning attic for project
2019-08-17 | 88.5 | Attic cleanup | In-Person | Luke Killeffer, David Killeffer, Peter Killeffer, Jonathan Killeffer, Benjamin Killeffer, Madison Killeffer, Thomas Killeffer, Sarah Killeffer, Robert Killeffer, Nick Fitzgerald, Jim Pozerski, Joe Cotter, Noah Struthers, Owen Bechtold, Jayden Bartrug, Jakob Khalil, Jim Shannon, James Shannon, | Cleaning up the attic and dismantling the pool table, HVAC system, etc.
2019-08-06 | 2 | Fundraiser research | email | Luke Killeffer | Talking to lowes on the phone about selling chocolates at entrance or exit for fundraiser
2019-08-17 | 24 | Attic cleanup | In-Person | Luke Killeffer, David Killeffer | shopping at Home Depot for tools/materials for project, and working at Legion on attic cleanup and subfloor installation
2019-08-17 | 54 | Attic cleanup | In-Person | Sarah Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer, Madison Killeffer, Thomas Killeffer | cleanup of Legion attic and trash removal
2019-08-18 | 2 | Painting, Attic cleanup | In-Person | Luke Killeffer, Peter Killeffer | Painted plywood insert for attic window insert, junk removal from attic
2019-08-21 | 57 | Attic cleanup and door installation | In Person | Luke Killeffer, Madison Killeffer, Peter Killeffer, Jonathan Killeffer, Ben Killeffer, Sarah Killeffer, David Killeffer, Joe Thompson | Replacing the airducts in the window frame with plywood and installing the door
2019-08-24 | 0.15 | Project photots | email | Luke Killeffer, David Killeffer | going over photos taken from the project
2019-07-10 | 7.5 | Attic cleanup | In-Person | Luke Killeffer, Sarah Killeffer, Ben Killeffer, Peter Killeffer | cleaning up trash from the attic
2019-07-10 | 35 | Attic cleanup | In-Person | Luke Killeffer, Sarah Killeffer, Peter Killeffer, Jonathan Killeffer, Benjamin Killeffer, Madison Killeffer, Thomas Killeffer | removing trash from attic into dumpster
2019-07-13 | 76 | Attic cleanup | In-Person | Robert Killeffer, David Killeffer, Luke Killeffer, Sarah Killeffer, Peter Killeffer, Jonathan Killeffer, Benjamin Killeffer, Madison Killeffer, Thomas Killeffer | removing trash from attic to dumpster, beginning disassembly of ductwork, many items brought to curb for giveaway
2019-07-09 | 2 | Research & Project Communications | Email | Luke Killeffer, David Killeffer, Ken Coburn | discussion of materials to use for project, requesting approval of materials, project scheduling, general project update communications
2019-07-11 | 1 | Research & Project Communications | Email, Discussion | Luke Killeffer, David Killeffer, Ken Coburn | Discussion about scheduling Project workdays, proejct plans
2019-08-13 | 1 | Project Communication | Email, Discussion | Luke Killeffer, David Killeffer, Scoutmaster Schultz | Emails to Troop requesting help on Eagle project workdays
2019-07-09 | 5 | Project Planning | In-Person Discussion | Luke Killeffer, David Killeffer, Sarah Killeffer | Discussion and project planning to get Luke back on track - developed project schedule, timeline, milestones, accountability, etc.
2019-09-07 | 6 | Completing the project | In-Person | Luke Killeffer, David Killeffer | Project Completion and complete installation of door
2019-09-01 | 0.5 | project planning | Email | Luke Killeffer, David Killeffer, Ken Coburn, Mr. Schultz | planning a work date for completing the project
2019-09-03 | 1 | project completion and cleanup | In-Person | Luke Killeffer, David Killeffer | painting cleanup, final room cleanup, etc.
2019-09-17 | 1 | reference letters | email | Luke Killeffer, David Killeffer, Johanna Thompson, Shannon Oteri | asking for reference letters
2019-09-22 | 0.15 | finalizing Proposal | email | Luke Killeffer, David Killeffer, Scoutmaster Schultz | going over photos taken from the project and what was written inside the workbook
| 613 | TOTAL HOURS